## Sheet1
Activities | Due Date | Who
Agree on the final pre-processing version | 2024-10-01 | All
Document the pre-processing code | 2024-10-31 | Ehsan
Apply 2 ML models, document the results and steps taken, and summarize the best results of each model in a table | 2024-10-31 | All
Validate the report (pre-processing step) | 2024-11-07 | Carlos, Stephen
Write the report with the interpretation of the two best models | 2024-11-15 | Carlos
Validate the report (interpretation step) | 2024-11-22 | Ehsan, Stephen
Write the conclusion | 2024-11-30 | Stephen
Validate the report (conclusion step) | 2024-12-04 | Carlos, Ehsan
Submit the report | 2024-12-05 | Carlos